- Pre-event checklist

| Key tasks to be arranged by the Event Coordinator | Who else should be involved? |  |  |
| --- | --- | --- | --- |
|  | Administrator | Course Setter | Caterer |
| Help the course setters choose a hash house site with suitable: - Access - Space for parking and camping (if required) - Space for hash house, admin and briefing - Toilets/area for port-a-loos/site for toilet pits - Water/bring water in - Power/bring generator |  |  |  |
| Recruit volunteers. Ensure volunteers know when and where to go. Let them know the policy for reimbursing expenses and where to find a claim form |  |  |  |
| Help the Administrator prepare the budget and entry form |  |  |  |
| Advertise event in newsletter and on website |  |  |  |
| Prepare Safety Plan and send a copy to the local authorities |  |  |  |
| Arrange to get flags, intention boards and navlights to the event site in time for hanging |  |  |  |
| Ensure forms and documents are prepared (with the help of the course setters and administrator): - Entry form - Final instructions - Map - Control card - Controls info sheet - Course setters notes - Flight plan intentions sheet |  |  |  |
| Print copies of event documents to hand out to participants. Also bring along extra copies of membership/newsletter forms and indemnity forms |  |  |  |
| Arrange to transport equipment to the event and to the sites where it is needed, e.g. water drop locations, all night café location |  |  |  |
| Arrange suitable vehicles for safety patrols, water drops, etc. |  |  |  |
| Arrange additional hired equipment such as port-a-loos and marquee |  |  |  |
| Track down the trophies with last year’s winners and ensure they will be at the event (NSW championships or Paddy Pallin) |  |  |  |
| If you need to reimburse volunteers or pay for any items at the event, ensure that cheques are written out in advance, or that the cheque book and two signatories will be handy at the event |  |  |  |

- Post-event checklist

| Key tasks to be arranged by the Event Coordinator | Who else should be involved? |  |  |
| --- | --- | --- | --- |
|  | Administrator | Course Setter | Caterer |
| Pack up and return equipment. Note any equipment issues with the equipment officer |  |  |  |
| Arrange flag collectors |  |  |  |
| Gather reports, stories and photos for the newsletter and website |  |  |  |
| Thank landowners and volunteers |  |  |  |
| Archive event documents – contact the NSWRA Archivist. At a minimum, you should archive: - Map – hard and electronic copies - Control list, course setters notes and final instructions – hard and electronic copies |  |  |  |
| Keep the Resources web pages up to date – let the webmaster know if you can add any useful information |  |  |  |