# SAFETY PLAN

for the

NSWRA

7th World Rogaining Championship 13th & 14th October 2006 Warrumbungle Moutains Australia

2006

Safety Plan prepared by: 	Alan  Mansfield

Signed:

Dated:

### TABLE OF CONTENTS

- Purpose of this Document

- Definition of Rogaining

- Involvement of Bushwalkers Rescue Squad in Search Operations

- Event Description

- Event Organisation Contact

- Risk Assessment

- Hazard Identification

- PURPOSE OF THIS DOCUMENT

This safety plan has been prepared to manage hazards in the NSWRA 7th World Rogaining Championships 13th & 14th October 2006 Warrumbungle Mountains Australia (hereafter called the Event).  It describes the Event and its location and provides contact and communication details for the Event organisers.  Hazards we are aware of are listed and classified. The measures that have been taken to reduce or eliminate each hazard are described.  The document also indicates the actions we propose to take if the identified hazards occur during the Event.

A copy of this document has been provided to the NSW Police Service at Coonabarabran, and to the principal individuals involved in the management of the Event.  In the eventuality of identified hazards, or other as yet unidentified hazards, occurring during the Event, it is proposed to implement this Safety Plan.

- DEFINITION OF ROGAINING

Rogaining is the sport of cross country navigation. It involves teams of two to five people travelling on foot and navigating only with a compass and a map prepared for the event.

Purpose:  Teams navigate cross country to checkpoints marked on the map and punch control cards. Checkpoint scores vary and the team amassing the highest score at the end of the event wins.

Duration:  Events range in duration from 6 to 24 hours and may include substantial night time competition.

Start & finish:  Takes place at the ‘Hash House’.  Competitors may camp there before (and after) the event and generally food will be provided during the event at the Hash House.

Equipment:  Generally Rogainers carry light weight equipment- day pack, food and water, sufficient clothing, torch and first aid.

- INVOLVEMENT OF BUSHWALKERS Wilderness RESCUE SQUAD IN SEARCH AND RESCUE OPERATIONS

The NSW Rogaining Association acknowledges that the NSW Police Service will be the peak agency supervising and co-ordinating any search, or search and rescue, requested at the Event.  Rogaine events are generally undertaken in rugged terrain, with few roads.  Search and rescue personnel must be physically fit, capable of operating for extended periods on foot, with limited support, during day and night time and in all weather conditions.  Strong navigation skills and personal survival skills are essential.

The NSW Rogaining Association considers that Bushwalkers Wilderness Rescue Squad are capable of providing search and rescue resources appropriate for use in Rogaining events, and request that Bushwalkers Wilderness Rescue Service Inc. are invited to assist in any search, or search and rescue, requested at the Event.

Bushwalkers Wilderness Rescue Squad is a member of the NSW Volunteer Rescue Association (VRA).

Contact:

Urgent Pager:	132 222		Ask for Pager No. 6277 321.

Leave a brief message including a return phone number

Mobile		0427 455 397

4	EVENT DESCRIPTION PAGE

| Name of the Event | NSWRA – 7th World Rogaining Championship 2006 Warrumbungle Mountains Australia |
| --- | --- |
| Date of the Event | 13th and 14th October 2006 |
| Event Start Time | 1200 13th October 2006 |
| Event Finish Time | 1200 14th October 2006 |
| Duration of Event | 24 hours |
| Location of the Event Administration (Hash House) | Education Centre, Camp Wallay |
| Course Location | Warrumbungle National Park park and surrounding farm land. See reference map |
| Vehicle Access to the Event course is from the following roads | Off Tooraweenah Road 36 kilometres from Coonababran at the turn off for the Warrumbungle National Park Visitor Centre |
| Location of the nearest helicopter landing site to Event Admin. | Camp Blackman |
| Approximate number of entrants at the Event | 700 |
| Approximate number of Event staff & volunteers | 60 |

5	EVENT ORGANISATION CONTACT PAGE

| ## Event is run by | NSW Rogaining Association |  |
| --- | --- | --- |
| Event Organiser | Alan Mansfield Ph Home 02 9797 6773 Mobile number (for the event only) 0422 292 194 or alternatively try satellite phone numbers as below in On-Course communication. Address 94 Greenhills Street Croydon Park NSW 2133 |  |
| Event Administrator | Ian Almond 220 Cordeaux Road Mount Kembla 2526 |  |
| Event Safety Officer |  |  |
| Network phone connections at Event Administration | Landline Nil Mobile Poor coverage Organisers mobile phone number 0418 638 425 Satelitte |  |
| On-Course communication | 0422 292 194 – Administration desk at Event Centre Satelitte ph |  |
| Emergency Services – all calls Police Ambulance Rural Fire Service | 000 |  |
| Police - Western Dubbo | #### Police NSW #### Coonabarabran 58 Dalgarno St 2357 (02) 6842 7299 Fax (02) 6842 7211 Baradine 17 Darling St 2396 (02) 6843 1808 Tooraweenah Bridge St 2831 (02) 6848 1044 Top of Form Bottom of Form Emergencies Or Crimes In Progress 000 Non-Emergencies/General Enquiries 13 1444 Regional Commands Western - Dubbo (02) 6881 3104 Police Headquarters Locked Bag 5102 Parramatta NSW 2124 13 1444 Emergencies Or Crimes In Progress 000 Non-Emergencies/General Enquiries 13 1444 Crime Stoppers FREECALL 1800 333 000 www.crimestoppers.com.au Police Online www.police.nsw.gov.au |  |
| ## Ambulance | #### Ambulance Service of NSW In An Emergency (Free Call) 000 www.ambulance.nsw.gov.au Ambulance Stations Stations may be unattended on Occasions Baradine Macquarie St 13 1233 Coonabarabran Cassilis St 13 1233 Administration Western Division Sector Office 62 Windsor Pde Dubbo 2830 (02) 6883 4333 Senior Complaints Officer 1800 269 133 | 13 1233 |
| Rural Fire Service | Rural Fire Service Castlereagh Zone Office (Warrumbungle/Gilgandra) 51 King St Coonabarabran 2357 (02) 6842 2645 |  |
| #### Westpac Rescue Helicopter Marketing & Media -- Tamworth | Operations Tamworth Airport (02) 6760 7744 Marketing & Media Shp28/ 341 Peel St Tamworth 2340 (02) 6766 6641 Top of Form Bottom of Form Marketing & Media Shp28/ 341 Peel St Tamworth 2340 (02) 6766 6641 Top of Form Bottom of Form Fax (02) 6766 7268 FREECALL 1800 155 155 Operations Tamworth Airport (02) 6760 7744 Fax (02) 6760 7747 chopper@rescuehelicopter.com.au www.rescuehelicopter.com.au |  |

6	RISK ASSESSMENT PAGE

Likelihood

| Level | Likelihood | Frequency |
| --- | --- | --- |
| 1 | Very Likely | NSW Rogaining Association does not have adequate data to make full assessment of the frequency of risks occurring. Based on experience and commonsense judgements, the range of frequencies is from “Likely to occur at every event” to “Very rare and not known to have happened” |
| 2 | Likely |  |
| 3 | Unlikely |  |
| 4 | Very Unlikely |  |

Consequence / Impact

| Level | Consequence or Impact |
| --- | --- |
| ##### A | Kill or cause permanent disability or ill health |
| B | Long term illness or serious injury |
| C | Medical Attention and several days off work |
| D | First Aid needed |

Level of Risk

| Consequence | Likelihood |  |  |  |
| --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 |
| #### A | Extreme | Extreme | High | Moderate |
| B | Extreme | High | High | Moderate |
| C | High | High | Moderate | Low |
| D | Moderate | Moderate | Low | Low |

7	HAZARD IDENTIFICATION

| Risk / Hazard | Level of Risk | What We Will Do To Eliminate or Minimise the Risk Prior to the Event | What We Will Do if the Hazard Occurs During the Event |
| --- | --- | --- | --- |
| ### Minor injuries and conditions |  | - Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course - Require each team to carry a first aid kit including a snake bite bandage - Have trained First Aiders with equipment on site. | In increasing order of seriousness, as appropriate to the situation: - Provide first aid as per St John Ambulance Australia book and/or refer to private medical practitioner - Evacuate to medical attention - Request emergency ambulance transport - Request immediate police and ambulance assistance for emergency rescue and evacuation |
| cuts & grazes | Moderate |  |  |
| Sprains | Moderate |  |  |
| objects in eye | Moderate |  |  |
| Fatigue | Moderate |  |  |
| ### Climate induced conditions |  |  |  |
| Dehydration | Moderate |  |  |
| heat stroke | Moderate |  |  |
| Hypothermia | Low |  |  |
| Asthma / allergic reactions | Moderate |  |  |
| sun burn | Moderate |  |  |
| ### Flora & Fauna |  |  |  |
| Snakes | Moderate |  |  |
| Ticks | Low |  |  |
| Leeches | Low |  |  |
| Stinging plants | Low |  |  |
| Livestock | Low |  |  |

- HAZARD IDENTIFICATION (Cont)

| Risk / Hazard | Risk Rating | What We Will Do To Eliminate or Minimise the Risk Prior to the Event | What We Will Do if the Hazard Occurs During the Event |
| --- | --- | --- | --- |
| Major injuries and conditions |  | - Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course - Maintain up to date information about weather conditions | In increasing order of seriousness, as appropriate to the situation: - Provide first aid as per St John Ambulance Australia book - Evacuate to medical attention - Request emergency ambulance transport - Request immediate police and ambulance assistance for emergency rescue and evacuation |
| Broken Bones | Moderate |  |  |
| Head Injuries | Low |  |  |
| Heart Attack | Low |  |  |
| Competitor hit by motor vehicle | Moderate |  |  |
| ###### Major incidents |  |  |  |
| Lost competitors | Moderate | - Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course - Advise participants that if they become lost they should await assistance and use a whistle to attract the attention of other participants or search parties. If possible, they should remain by a track. | In increasing order of seriousness, as appropriate to the situation: - Assess information obtained from manned checkpoint, intention sheets and other sources - Instigate road/track search by vehicle - Instigate ground search of probable areas with existing Rogaine Association personnel resources - Request police assistance for search / search and rescue - Request Bushwalkers Rescue Squad involvement in search activities |
| Major incidents (continued) |  |  |  |
| Competitor injured and in need of evacuation | Moderate | - Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course - Provide information about the manned checkpoint on the course so team mates of injured party can seek assistance | In increasing order of seriousness, as appropriate to the situation: - Provide first aid as per St John Ambulance Australia book - Evacuate to medical attention - Request immediate ambulance transport - Request immediate police and ambulance assistance for emergency rescue and evacuation - Request police assistance in search /search and rescue |
| Major Environmental Events |  |  |  |
| Bushfires | Moderate | - Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course and appropriate actions for competitors on the course if confronted by the hazard. - Maintain up to date information about weather conditions. | - Contact NSW Rural Fire Service and request assistance. - Evacuate to safe ground |
| Floods | Low |  | - Course is unlikely to be severely affected by heavy rain. - Event will proceed with cautions given to competitors |

See attachments – medical services list and outline map of rogaine.

- MEDICAL SERVICES

Coonabarabran Health Service (Hospital)

101-103 Edwards Street

Coonabarabran NSW 2357

Phone (02)6842 2211

# Coonabarabran Community Health Care

Cassilis Street

Coonabarabran NSW 2357

Phone (02) 6842 6426

# Coonabarabran Medical Centre

61 Cassilis Street

Coonabarabran NSW 2357

Dr Milton and Dr Salim

Phone (02) 6842 3366

# Family Medical Centre

Strand Arcade

Coonabarabran NSW 2357

Dr Larnach

Phone (02) 6842 3033

# Warrumbungle Medical Centre

59 Cassilis Street

Coonabarabran NSW 2357

Dr Iannuzzi and Dr Tsironis

Phone (02) 6842 3333

# Dental Centre

70 Cassilis Street

Coonabarabran NSW 2357

Dr Raadgever

Phone (02) 6842 1396

- Outline map of course