# RISK & SAFETY PLAN

for the

NSWRA

NSW Rogaining Championships

22nd/23rd September 2018

Abercrombie River National Park

Safety Plan prepared by: 	Michael Watts					Checked by:

Signed:										Signed:

Dated: 										Checked:

### TABLE OF CONTENTS					1.  Purpose of this Document

2.  Definition of Rogaining

3.  Involvement of NSW Police Service in Search Operations

4.  Event Description

5.  Event Organisation Contact

6.  Risk Assessment

7.  Hazard Identification

- PURPOSE OF THIS DOCUMENT

This safety plan has been prepared to manage hazards in the 2018 NSW Rogaining Championships to be held in Abercrombie River National Park (ARNP) over the weekend of the 22nd and 23rd of September 2018 (hereafter called the Event). The Administration centre for the event is located adjacent to the ARNP entrance on Abercrombie Fire Trail, on the western boundary of the ARNP.  It describes the Event and its location and provides contact and communication details for the Event organisers. Hazards we are aware of are listed and classified. The measures that have been taken to reduce or eliminate each hazard are described. The document also indicates the actions we propose to take if the identified hazards occur during the Event.

A copy of this document is provided to NSW Police Goulburn Area Command, the NSW National Parks & Wildlife Service, the local RFS and SES brigades at Burraga, Neil Francis (landholder), NSW Ambulance Service, Bush Search and Rescue (BSAR) and to the principal individuals involved in the management of the Event. In the eventuality of identified hazards, or other as yet unidentified hazards, occurring during the Event, it is proposed to implement this Safety Plan.

- DEFINITION OF ROGAINING

Rogaining is the sport of long distance cross country navigation similar to orienteering. It involves teams of two to five people travelling on foot and navigating only with a compass and a map prepared for the event. There is no fixed route, with teams able to determine their own individual movements around the course.

Purpose: In this event, teams navigate to checkpoints marked on the map. Presence at the checkpoint is recorded electronically with a wrist mounted device. Checkpoints are given scores which vary from checkpoint to checkpoint, generally worth between 10 and 100 points. The team amassing the highest score within the time period allocated for the event wins. Teams lose points if they are late to finish.

Duration: This event includes 8 and 24 hour duration classes. Both classes start at 12:00 noon on Sat 22nd September. The 8 hour class finishes at 8:00pm on Sat 22nd September. The 24 hour class finishes at 12:00 noon on Sunday 23rd September.

Start & finish: Takes place at the ‘Hash House’ located adjacent to the ARNP western entrance on Abercrombie Fire Trail. Food will be provided for participants from approximately 5:00pm on Saturday until approximately 2:00pm on Sunday.

Equipment: Rogainers carry light weight equipment – map, compass, and typically a day pack with food and water, sufficient clothing, and first aid (mandatory items are a whistle, space blanket and snake bandage)  sufficient for the duration. Locations where participants can resupply water are marked on the map.

Facilities: Participants are provide with a map of the course area, with the control locations pre-marked; control description and course notes.

- SEARCH AND RESCUE OPERATIONS

The NSW Rogaining Association acknowledges that SES BSAR will be the responsible first responders, and will request outside assistance as required. The NSW Police Service will be the peak agency supervising and co-ordinating any emergency search, or search and rescue, requested by BSAR. Access to the course area is from public roads. Access within the course area is by a combination of roads, fire trails, walking tracks and cross-country travel. Event participants are NOT required to remain on trails marked on the event map.  The nature of the event means there are several ideally skilled personnel available to assist in any search and rescue operation.

4	EVENT DESCRIPTION PAGE

| Name of the Event | NSW Rogaining Championships |
| --- | --- |
| Date of the Event | Saturday 22nd September 2018; Sunday 23rd September 2018 |
| Event Start Time | 12:00 noon on Saturday 22nd September |
| Event Finish Time | 8 hours: 8:00pm on Saturday 22nd September; 24 hours: 12:00 noon on Sunday 23rd September |
| Duration of Event | 8 hours or 12 hours |
| Location of the Event Administration (Hash House) | Abercrombie River National Park western entrance, on Abercrombie Fire Trail. Abercrombie Fire Trail runs off Emden Vale Road. The GPS coordinates of the Hash House (HH) are: Latitude: -34.089547 Longitude: 149.619990 Units are decimal degrees. The NSW Lands Department Maps are ARKSTONE 8829-4N and FULLERTON 8829-4S The MGA grid coordinates of the Hash House (HH) are: Block 55 H 07 41 727 (Easting) and 62 24 816 (Northing) |
| Course Location | The rogaine course lies wholly with Abercrombie River National Park |
| Vehicle Access to the Event course is from the following routes | Access to the Hash House for 2WD vehicles is possible from the following locations: Abercrombie Fire Trail Access to the National Park for 4WD vehicles is possible from the following locations: Emden Vale Road and Abercrombie Fire Trail Felled Timber Rd and Middle Fire Trail |
| Location of the nearest helicopter landing site to Event Admin. | Approximately 350 metres from the HH site, adjacent to Abercrombie Fire Trail. The GPS coordinates of the proposed helicopter landing site are: Latitude: -34.086575 Longitude: 149.620291 Units are decimal degrees. The NSW Lands Department Maps are ARKSTONE 8829-4N and FULLERTON 8829-4S The MGA grid coordinates of the Hash House (HH) are: Block 55 H 07 41 764 (Easting) and 62 25 156 (Northing) |
| Approximate number of entrants at the Event | Approximately 200 to 250 entrants are expected based on recent years attendances. |
| Approximate number of Event staff & volunteers | 20 |

5	EVENT ORGANISATION CONTACT PAGE

| Event is run by | NSW Rogaining Association Inc - President: Trevor Gollan (tgollan@gmail.com) |
| --- | --- |
| Chief Event Coordinator/Setter | Michael Watts 0419 626 077 michaeljwatts@optusnet.com.au |
| Event Administrator | Anita Bickle 0434 369 493 admin@nswrogaining.org |
| Event First Aid Officer | SES BSAR On-Site coordinator Geoff Dale Mobile: 0419 290 417 |
| Network phone connections at Event Administration | Michael Watts Mobile: 0419 626 077 Phone connection details to be confirmed |
| On-Course communication | Mobile phone coverage is available on certain high points along ridge lines in the course area. Participants are encouraged to carry a mobile phone, with the “Emergency+” app installed. |
| Emergency Services – all calls Police / Ambulance / Fire | 000 (or 112 with a mobile phone) |
| Police located close to the event | Chifley Police District 139 Rankin St Bathurst 2795 Tel: (02) 6332 8699 Fax: (02) 6332 8611 Oberon Police Station (Note: this is not open 24 hours) 77 Queen St Oberon NSW 2787 Tel: (02) 6336 1000 Fax: (02) 6336 0015 |

6	RISK ASSESSMENT PAGE

Likelihood

| Level | Likelihood | Frequency |
| --- | --- | --- |
| 1 | Very Likely | NSW Rogaining Association does not have adequate data to make full assessment of the frequency of risks occurring. Based on experience and commonsense judgements, the range of frequencies is from “Likely to occur at every event” to “Very rare and not known to have happened” |
| 2 | Likely |  |
| 3 | Unlikely |  |
| 4 | Very Unlikely |  |

Consequence / Impact

| Level | Consequence or Impact |
| --- | --- |
| A | Kill or cause permanent disability or ill health |
| B | Long term illness or serious injury |
| C | Medical Attention and several days off work |
| D | First Aid needed |

Level of Risk

|  | LIKELIHOOD |
| --- | --- |
| CONSEQUENCE / IMPACT | 1. Very Likely | 2. Likely | 3. Unlikely | 4. Very Unlikely |
| A. Kill or cause permanent injury | Extreme | Extreme | High | Moderate |
| B. Long-term illness or serious injury | Extreme | High | High | Moderate |
| C. Medical attention and several days off work | High | High | Moderate | Low |
| D. First Aid needed | Moderate | Moderate | Low | Low |

7	HAZARD IDENTIFICATION

| Risk / Hazard | Level of Risk | What We Will Do To Eliminate or Minimise the Risk Prior to the Event | What We Will Do if the Hazard Occurs During the Event |
| --- | --- | --- | --- |
| Minor injuries and conditions | Provide written information to competitors before the event and verbally immediately prior to the event (and after the event if necessary) about conditions and hazards on the course Reinforce drink to thirst. Do not under- or over-hydrate Request participants to leave a copy of their proposed route with organizers Request participants each carry an emergency whistle and space blanket and each team carry a first aid kit incorporating two snake bandages Have trained First Aider with equipment on site. Instruct competitors to exercise their own duty of care to self and others during the event Promote use of mobile phones for emergency communication. Be ready (hiking pack with shelter and equipment) to take a vehicle into the course area should any competitor require assistance | In increasing order of seriousness, as appropriate to the situation: Provide vehicle transport back to the event administration centre Provide first aid through BSAR Evacuate to medical attention to Bathurst Base Hospital (or possibly Lithgow Base Hospital). Request emergency ambulance transport Request immediate police and ambulance assistance for emergency rescue and evacuation |
| Cuts & grazes (1-D) | Moderate |  |  |
| Sprains (2-D) | Moderate |  |  |
| Objects in eye (3-D) | Low |  |  |
| Fatigue (2-D) | Moderate |  |  |
| Climate induced conditions |  |  |
| Dehydration (2-D) | Moderate |  |  |
| Hyponatremia (3-C) | Moderate |  |  |
| Heat stroke (3-C) | Moderate |  |  |
| High creek crossings after rain (4-C) | Low |  |  |
| Hypothermia (4-C) | Low |  |  |
| Asthma/allergic reactions (3-D) | Low |  |  |
| Dangerous track surface (4-c) | Low |  |  |
| Sun burn (2-D) Moderate |  |  |
| Flora & Fauna |  |  |
| Snakes (4-B) | Moderate |  |  |
| Ticks (3-D) | Low |  |  |
| Leeches (3 -D) | Low |  |  |
| Stinging plants (3-D) | Low |  |  |
| Livestock (4-C) | Low |  |  |
| Feral Animals (4-C) | Low |  |  |

HAZARD IDENTIFICATION (Cont’d)

| Risk / Hazard | Risk Rating | What We Will Do To Eliminate or Minimise the Risk Prior to the Event | What We Will Do if the Hazard Occurs During the Event |
| --- | --- | --- | --- |
| Major injuries and conditions |
| Broken Bones (4-B) | Moderate | Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course. Promote use of mobile phones for emergency communication. Promote the principle of teamwork, that the team stay together in case of an emergency. Request participants each carry an emergency whistle and space blanket and each team carry a first aid kit incorporating two snake bandages | In increasing order of seriousness, as appropriate to the situation: Provide vehicle transport back to the event administration centre Provide first aid through BSAR Evacuate to medical attention to Bathurst Base Hospital (or possibly Lithgow Base Hospital). Request emergency ambulance transport Request immediate police and ambulance assistance for emergency rescue and evacuation |
| Head Injuries (4-A) | Moderate |  |  |
| Heart Attack (4-A) | Moderate |  |  |
| Competitor hit by motor vehicle (4-A) | Moderate |  |  |
| Fall from high places (4 - A) | Moderate |  |  |

HAZARD IDENTIFICATION (Cont’d)

| Risk / Hazard | Risk Rating | What We Will Do To Eliminate or Minimise the Risk Prior to the Event | What We Will Do if the Hazard Occurs During the Event |
| --- | --- | --- | --- |
| Major incidents |  |
| Late / Lost competitors (3 – C) | Moderate | Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course. Advise participants that if they become lost they should stay together as a team, await assistance and use a whistle to attract the attention of other participants or search parties. If possible, they should remain by or get to a road. Recommend each team carry a mobile phone. Provide mobile phone numbers on maps. Request participants each carry an emergency whistle and space blanket and each team carry a first aid kit incorporating two crepe bandages | In increasing order of seriousness, as appropriate to the situation: 30 mins late – administration reports that team is missing; team is announced missing at hash house, and asks other teams if they were recently seen. Refer to team’s proposed route. 45 mins – look for the team’s car. Try the team’s phone number. 60 mins – BSAR to mobilise a road search on the appropriate part of the course using event organisers and participants, referring to team’s flight plan 4 hours – notify National Parks and Police 6 hours – request police assistance for search and rescue. |

HAZARD IDENTIFICATION (Cont’d)

| Risk / Hazard | Risk Rating | What We Will Do To Eliminate or Minimise the Risk Prior to the Event | What We Will Do if the Hazard Occurs During the Event |
| --- | --- | --- | --- |
| Major incidents (cont’d) |  |
| Competitor injured and in need of evacuation from course (3 – C) | Moderate | Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course. Recommend each team carry a mobile phone. Provide mobile phone numbers on maps. Request participants each carry an emergency whistle and space blanket and each team carry a first aid kit incorporating two crepe bandages Instruct competitors to exercise their own duty of care to self and others during the event | In increasing order of seriousness, as appropriate to the situation: BSAR to provide first aid Evacuate to medical attention Request immediate ambulance transport Request police and ambulance assistance for search/search and rescue |
| Competitor injured and in need of evacuation from event headquarters (3 – D) | Low | Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course Request participants each carry an emergency whistle and space blanket and each team carry a first aid kit incorporating two crepe bandages Ensure qualified first aiders are present at event headquarters | In increasing order of seriousness, as appropriate to the situation: BSAR to provide first aid Evacuate to medical attention Request immediate ambulance transport Request police and ambulance assistance for search/search and rescue |

HAZARD IDENTIFICATION (Cont’d)

| Risk / Hazard | Risk Rating | What We Will Do To Eliminate or Minimise the Risk Prior to the Event | What We Will Do if the Hazard Occurs During the Event |
| --- | --- | --- | --- |
| Major Environmental Events |
| Bushfires | Low | Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course and appropriate actions for competitors on the course if confronted by the hazard. Maintain up to date information about weather conditions. | Contact NSW Rural Fire Service and NSW National Parks and Wildlife Service and request assistance. Evacuate to safe ground on recommendation of NSW Rural Fire Service. |
| Floods | Low |  | If heavy, prolonged rain occurs immediately before the event, some tracks may be marked Out of Bounds. Cautions will be given to competitors at the briefing if rain is forecast |