# SAFETY PLAN

for the

NSWRA

NSW Championship Rogaine 2005

2005

Safety Plan prepared by: 	Alan  Mansfield (Event coordinator & Safety Officer)

Signed:

Dated:

### TABLE OF CONTENTS

- Purpose of this Document

- Definition of Rogaining

- Involvement of Bushwalkers Rescue Squad in Search Operations

- Event Description

- Event Organisation Contact

- Risk Assessment

- Hazard Identification

- PURPOSE OF THIS DOCUMENT

This safety plan has been prepared to manage hazards in the NSWRA Social Rogaine 2005 – 15th and 16th October 2005 (hereafter called the Event).  It describes the Event and its location and provides contact and communication details for the Event organisers.  Hazards we are aware of are listed and classified. The measures that have been taken to reduce or eliminate each hazard are described.  The document also indicates the actions we propose to take if the identified hazards occur during the Event.

A copy of this document has been provided to the NSW Police Service at Kandos and Rlystone, and to the principal individuals involved in the management of the Event.  In the eventuality of identified hazards, or other as yet unidentified hazards, occurring during the Event, it is proposed to implement this Safety Plan.

- DEFINITION OF ROGAINING

Rogaining is the sport of cross country navigation. It involves teams of two to five people travelling on foot and navigating only with a compass and a map prepared for the event.

Purpose:  Teams navigate cross country to checkpoints marked on the map and punch control cards. Checkpoint scores vary and the team amassing the highest score at the end of the event wins.

Duration:  Events range in duration from 6 to 24 hours and may include substantial night time competition.

Start & finish:  Takes place at the ‘Hash House’.  Competitors may camp there before (and after) the event and generally food will be provided during the event at the Hash House.

Equipment:  Generally Rogainers carry light weight equipment- day pack, food and water, sufficient clothing, torch and first aid.

- INVOLVEMENT OF BUSHWALKERS Wilderness RESCUE SQUAD IN SEARCH AND RESCUE OPERATIONS

The NSW Rogaining Association acknowledges that the NSW Police Service will be the peak agency supervising and co-ordinating any search, or search and rescue, requested at the Event.  Rogaine events are generally undertaken in rugged terrain, with few roads.  Search and rescue personnel must be physically fit, capable of operating for extended periods on foot, with limited support, during day and night time and in all weather conditions.  Strong navigation skills and personal survival skills are essential.

The NSW Rogaining Association considers that Bushwalkers Wilderness Rescue Squad are capable of providing search and rescue resources appropriate for use in Rogaining events, and request that Bushwalkers Wilderness Rescue Service Inc. are invited to assist in any search, or search and rescue, requested at the Event.

Bushwalkers Wilderness Rescue Squad is a member of the NSW Volunteer Rescue Association (VRA).

Contact:

Urgent Pager:	132 222		Ask for Pager No. 6277 321.

Leave a brief message including a return phone number

Mobile		0427 455 397

4	EVENT DESCRIPTION PAGE

| Name of the Event | NSWRA – NSW Championship 2005 |
| --- | --- |
| Date of the Event | 15th and 16th October 2005 |
| Event Start Time | 1200 15th October 2005 |
| Event Finish Time | 1200 16th October 2005 |
| Duration of Event | 24 hours plus lesser events of 6 hours and 15 in 24 hours |
| Location of the Event Administration (Hash House) | UTM 56H 239315 E 63 61170N WGS 84 32 51. 396S 150 12.862E Located on lot 45 off Narango Road adjacent to Ganguddy Creek |
| Course Location | Private land, Nullo Stae Forest and Wollemi National Park (Dunn’s Swamp locale) – Olinda 1: 25 000 Land Information Centre Map; Map number 89 – 3 – N The rogaining course boundaries are approximately bounded by 32 52 30 150 10 00 – 32 52 30 150 15 00 – 32 46 00 150 10 00 – 32 46 00 150 15 00 This can be can described as bounded by Nullo Mountain Road to the West, Narango Road to the South, Coxes Creek Road to the North. Centred on the locales Never Never, Ganguddy and Kelgoola |
| Vehicle Access to the Event course is from the following roads | “Once you are at Rylstone From the Rylstone Hospital (on the road to Kandos), turn at the large sign to Wollemi National Park. Continue on this sealed road, taking the left fork to Dunn's Swamp, for around 18 km (there are several dips, so take care). Stay on this road after it turns to gravel, and continue past the left turn to Dunn's swamp for about 1 km to the hash house.” |
| Location of the nearest helicopter landing site to Event Admin. | UTM 56H 239315 E 63 61170N WGS 84 32 51. 396S 150 12.862E |
| Approximate number of entrants at the Event | 300 |
| Approximate number of Event staff & volunteers | 30 |

5	EVENT ORGANISATION CONTACT PAGE

| ## Event is run by | NSW Rogaining Association |  |
| --- | --- | --- |
| Event Organiser | Alan Mansfield Ph Home 02 9797 6773 Mobile number (for the event only) 0418 638 425 or alternatively try satellite phone numbers as below in On-Course communication. Address 94 Greenhills Street Croydon Park NSW 2133 |  |
| Event Administrator | David and Jane McKenna Ph Home 02 9713 9334 Address 20 / 1 Abbotsford Cove Drive, Abbotsford NSW 2046 |  |
| Event Safety Officer | Alan Mansfield Ph Home 02 9797 6773 Mobile number (for the event only) 0418 638 425 Address 94 Greenhills Street Croydon Park NSW 2133 |  |
| Network phone connections at Event Administration | Landline Nil Mobile Poor coverage Organisers mobile phone number 0418 638 425 Satelitte |  |
| On-Course communication | Participants will be provided with the organiser’s CDMA / Satelitte - 0147 148 005 and 0147 148 006 |  |
| Emergency Services – all calls Police Ambulance Rural Fire Service | 000 |  |
| Police - Western Dubbo | Rylstone 89 Louee Street NSW 2849 Phone 02 6379 1000 Facsimile 02 6379 1326 |  |
| ## Ambulance | 000 Illford Street Rlystone NSW | 13 1233 |
| Rural Fire Service – Wingecarribee Fire Control Centre | Mid Western Office (Mudgee/Rylstone) Depot Road Mudgee 2850 (02) 6372 4434 |  |

6	RISK ASSESSMENT PAGE

Likelihood

| Level | Likelihood | Frequency |
| --- | --- | --- |
| 1 | Very Likely | NSW Rogaining Association does not have adequate data to make full assessment of the frequency of risks occurring. Based on experience and commonsense judgements, the range of frequencies is from “Likely to occur at every event” to “Very rare and not known to have happened” |
| 2 | Likely |  |
| 3 | Unlikely |  |
| 4 | Very Unlikely |  |

Consequence / Impact

| Level | Consequence or Impact |
| --- | --- |
| ##### A | Kill or cause permanent disability or ill health |
| B | Long term illness or serious injury |
| C | Medical Attention and several days off work |
| D | First Aid needed |

Level of Risk

| Consequence | Likelihood |  |  |  |
| --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 |
| #### A | Extreme | Extreme | High | Moderate |
| B | Extreme | High | High | Moderate |
| C | High | High | Moderate | Low |
| D | Moderate | Moderate | Low | Low |

7	HAZARD IDENTIFICATION

| Risk / Hazard | Level of Risk | What We Will Do To Eliminate or Minimise the Risk Prior to the Event | What We Will Do if the Hazard Occurs During the Event |
| --- | --- | --- | --- |
| ### Minor injuries and conditions |  | - Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course - Require each team to carry a first aid kit including a snake bite bandage - Have trained First Aiders with equipment on site. | In increasing order of seriousness, as appropriate to the situation: - Provide first aid as per St John Ambulance Australia book and/or refer to private medical practitioner - Evacuate to medical attention - Request emergency ambulance transport - Request immediate police and ambulance assistance for emergency rescue and evacuation |
| cuts & grazes | Moderate |  |  |
| Sprains | Moderate |  |  |
| objects in eye | Moderate |  |  |
| Fatigue | Moderate |  |  |
| ### Climate induced conditions |  |  |  |
| Dehydration | Moderate |  |  |
| heat stroke | Moderate |  |  |
| Hypothermia | Low |  |  |
| Asthma / allergic reactions | Moderate |  |  |
| sun burn | Moderate |  |  |
| ### Flora & Fauna |  |  |  |
| Snakes | Moderate |  |  |
| Ticks | Low |  |  |
| Leeches | Low |  |  |
| Stinging plants | Low |  |  |
| Livestock | Low |  |  |

- HAZARD IDENTIFICATION (Cont)

| Risk / Hazard | Risk Rating | What We Will Do To Eliminate or Minimise the Risk Prior to the Event | What We Will Do if the Hazard Occurs During the Event |
| --- | --- | --- | --- |
| Major injuries and conditions |  | - Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course - Maintain up to date information about weather conditions | In increasing order of seriousness, as appropriate to the situation: - Provide first aid as per St John Ambulance Australia book - Evacuate to medical attention - Request emergency ambulance transport - Request immediate police and ambulance assistance for emergency rescue and evacuation |
| Broken Bones | Moderate |  |  |
| Head Injuries | Low |  |  |
| Heart Attack | Low |  |  |
| Competitor hit by motor vehicle | Moderate |  |  |
| ###### Major incidents |  |  |  |
| Lost competitors | Moderate | - Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course - Advise participants that if they become lost they should await assistance and use a whistle to attract the attention of other participants or search parties. If possible, they should remain by a track. | In increasing order of seriousness, as appropriate to the situation: - Assess information obtained from manned checkpoint, intention sheets and other sources - Instigate road/track search by vehicle - Instigate ground search of probable areas with existing Rogaine Association personnel resources - Request police assistance for search / search and rescue - Request Bushwalkers Rescue Squad involvement in search activities |
| Major incidents (continued) |  |  |  |
| Competitor injured and in need of evacuation | Moderate | - Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course - Provide information about the manned checkpoint on the course so team mates of injured party can seek assistance | In increasing order of seriousness, as appropriate to the situation: - Provide first aid as per St John Ambulance Australia book - Evacuate to medical attention - Request immediate ambulance transport - Request immediate police and ambulance assistance for emergency rescue and evacuation - Request police assistance in search /search and rescue |
| Major Environmental Events |  |  |  |
| Bushfires | Moderate | - Provide written information to competitors before the event and verbally immediately prior to the event about conditions and hazards on the course and appropriate actions for competitors on the course if confronted by the hazard. - Maintain up to date information about weather conditions. | - Contact NSW Rural Fire Service and request assistance. - Evacuate to safe ground |
| Floods | Low |  | - Course is unlikely to be severely affected by heavy rain. - Event will proceed with cautions given to competitors |

